## Sheet1
No | Task | Start Date | End Date | Duration | Slack | Status
1 | Feasibility Study | 2015-09-18 | 2015-09-25 | 6 | 2 | Completed
2 | Study of structure of files | 2015-09-25 | 2015-10-05 | 8 | 3 | Completed
3 | Implementation of generic file generator - phase 1 | 2015-09-25 | 2015-10-08 | 12 | 2 | Completed
4 | User Interface Design - phase 1 | 2015-09-26 | 2015-10-12 | 14 | 3 | Completed
5 | Presentation #1 | 2015-10-12 | 2015-10-21 | 8 | 2 | Completed
6 | Usability Test | 2015-10-26 | 2015-10-31 | 3 | 2 | Completed
7 | Implementation study of structure of files - phase 2 | 2015-10-19 | 2015-10-31 | 11 | 2 | Completed
8 | Iterative implementation - phase 2 | 2015-10-16 | 2015-11-02 | 16 | 2 | Completed
9 | Test the enhanced product - phase 2 | 2015-10-30 | 2015-11-04 | 4 | 2 | Completed
10 | Presentation #2 | 2015-11-02 | 2015-11-06 | 3 | 1 | Completed
11 | Report 2 | 2015-11-02 | 2015-11-06 | 6 | 2 | Completed
12 | Configuration text editor | 2015-11-02 | 2015-11-16 | 10 | 4 | In progress
13 | User testing | 2015-11-07 | 2015-11-16 | 8 | 2 | In progress
14 | Client testing | 2015-11-14 | 2015-11-21 | 6 | 2 | In progress
15 | Review of final project | 2015-11-20 | 2015-11-28 | 6 | 2 | New
16 | Final presentation #3 | 2015-11-22 | 2015-12-04 | 8 | 4 | New
17 | Report 3 | 2015-11-30 | 2015-12-04 | 6 | 2 | New
18 | Delivery of project | 2015-12-05 | 2015-12-12 | 5 | 2 | New